## Summary
Grant-Admin Support Sample
No-charge validation artifact. Support-only: no legal advice, procurement advice, portal credentials, official submission, or payment request.
Control | Value | Workbook Sections | Purpose
Status | no-charge validation | Reimbursement Tracker | Track workstreams, source documents, owners, support boundaries, and missing-evidence risk.
Proof Status | $0 - workflow proof only | Document Checklist | Review whether key grant, budget, procurement, invoice, payment, and retention records exist.
Outreach Performed | False | Risk Log | Keep deadline, package, compliance, and reviewer qualification risks visible.
Portal Action Performed | False | CFR Evidence Map | Map support outputs to 2 CFR / HUD / CDBG evidence areas without giving legal opinions.
Payment Requested | False | Source Change Log | Track public addenda, package changes, guidance refreshes, and workbook sections affected by source changes.
Sample Decision | support_only_validation_ready | Approval Dependencies | Keep FloridaCommerce, HUD/CDBG, official submission, and validation-gate dependencies explicit.
Approval Gate | Approve one qualified grant-admin validation ask | Closeout Tracker | Map annual submissions, final closeout, retention, monitoring, and public-records handoff evidence.
|  | Validation Questions | Capture whether a qualified reviewer thinks the support packet is useful, risky, generic, or worth narrowing.
|  | Checks | Audit workbook counts, scope gates, and proof status.
Hard Boundaries | Status
No prime grant-administrator bid | Required
No legal advice | Required
No procurement advice | Required
No official grant reporting | Required
No portal credential handling | Required
No official submission | Required
No compliance certification | Required
No payment request | Required
No cold outreach | Required

## Reimbursement Tracker
Reimbursement Tracker
Sample tracker rows from the support-only grant-admin packet.
Tracker ID | Workstream | Support Task | Source Documents Needed | Owner | Andy Support Boundary | Status | Risk If Missing | Reviewer Usefulness | Reviewer Notes
rt-001 | grant agreement and budget setup | Create a control sheet mapping approved grant budget lines to internal workstreams and reimbursement categories. | grant agreement or award notice; approved project budget; eligible cost category list; internal project work breakdown | qualified grant administrator or client project owner | Build the tracker structure and reconcile fields; do not determine legal eligibility. | sample_not_started | Costs may be coded inconsistently before reimbursement requests.
rt-002 | procurement file evidence | Track whether each contract or vendor file has procurement method, solicitation record, evaluation record, award record, and contract reference. | procurement policy reference; solicitation or quote record; evaluation or selection record; executed contract; required contract-provision checklist | qualified grant administrator or procurement owner | Organize evidence status and missing-document flags; do not approve procurement compliance. | sample_not_started | Reimbursement or audit file may lack support for procurement history.
rt-003 | invoice and payment packet | Create a reimbursement packet index linking invoice, contract line, proof of payment, acceptance/inspection note, and budget line. | vendor invoice; contract or purchase order; pay application if applicable; proof of payment; acceptance or inspection evidence; budget line mapping | qualified grant administrator or finance owner | Reconcile invoice packet completeness and math; do not certify cost allowability. | sample_not_started | Payment may be difficult to tie to an eligible approved cost.
rt-004 | change order and scope drift | Track changes to scope, budget, schedule, and evidence required before reimbursement. | change order; approval record; updated budget or schedule; supporting cost detail; grant-administrator review note | qualified grant administrator or project owner | Flag changes and organize support; do not decide whether changes are grant-eligible. | sample_not_started | Scope or cost changes may not be supported at reimbursement or audit time.
rt-005 | draw request package | Prepare an internal readiness checklist before the qualified administrator submits or approves a reimbursement/draw package. | reimbursement request draft; supporting invoice index; proof-of-payment index; budget-to-actual tracker; open issue log | qualified grant administrator | Prepare readiness view only; no official submission or approval. | sample_not_started | Submission package may be late, incomplete, or difficult to review.

## Document Checklist
Source-Document Checklist
Completeness review only. This sheet does not certify compliance or allowability.
Check ID | Document | Why Needed | Support Status | Boundary | Received? | Missing Detail | Reviewer Notes
doc-001 | grant agreement or award notice | Establishes award basis, program rules, budget, period, and responsible parties. | required_reference | Do not interpret legal terms; mark where terms control tracker fields.
doc-002 | approved budget and budget amendments | Connects reimbursement categories to approved funding limits. | required_reference | Track budget-to-actual; do not approve eligibility.
doc-003 | procurement file | Supports vendor selection history and required federal-award records. | required_reference | Flag missing files; do not certify procurement compliance.
doc-004 | executed contracts and contract-provision checklist | Links vendor work to required contract clauses and scope. | required_reference | Index clauses and evidence status; do not provide legal review.
doc-005 | invoice, payment, and acceptance evidence | Supports reimbursement package completeness. | required_reference | Reconcile source docs; do not certify allowability.
doc-006 | audit and retention index | Keeps reimbursement support traceable for later review. | recommended_reference | Organize records; do not set official retention policy.

## Risk Log
Deadline and Risk Log
Use this sheet to keep validation risks explicit before any paid or official work.
Risk ID | Risk | Source | Impact | Mitigation | Severity | Open? | Reviewer Notes
risk-001 | Response due date is close | JEA current bid openings | Prime response is not realistic without established grant-admin qualifications and package review. | Use as support-sample validation, not a prime bid. | High | Yes
risk-002 | Zycus package controls details | JEA current bid openings | Minimum qualifications, evaluation matrix, and forms may materially change support needs. | Do not finalize paid scope until package details are reviewed. | High | Yes
risk-003 | Federal-award compliance risk | HUD and 2 CFR Part 200 | Support work can drift into legal/procurement/compliance advice. | Keep support limited to trackers, checklists, evidence organization, and math/reconciliation. | High | Yes
risk-004 | Qualified reviewer requirement | route decision matrix | A generic owner review will not prove usefulness for grant-admin buyers. | Only validate with a qualified grant administrator, public-sector consultant, or municipal finance/grants operator. | High | Yes

## CFR Evidence Map
2 CFR / CDBG Evidence Map
Map evidence areas to support outputs without making compliance or legal representations.
Area | Source Anchor | Sample Support Output | Boundary | Reviewer Concern | Safe To Use?
procurement standards | HUD CDBG-DR FAQ references 2 CFR procurement sections | procurement file completeness tracker | No procurement compliance opinion
contract provisions | HUD CDBG-DR FAQ references required contract clauses | contract-provision evidence index | No legal review of clauses
cost principles | 2 CFR Part 200 includes cost principles | budget-to-invoice mapping and exception log | No allowability certification
audit readiness | 2 CFR Part 200 includes audit requirements | source-document index and retention handoff checklist | No official audit representation

## Source Change Log
Source Change Log
Track public-source changes before a reviewer relies on the workbook.
Change ID | Source | Change Type | Public-Source Evidence | Support Action | Boundary | Reviewer Status | Reviewer Notes
chg-001 | City of Avon Park RFP #26-05 public RFP page | addendum and public-source update tracking | Public RFP pages and supporting documents can change through addenda before submission deadlines. | Track last public-source check, addendum number if visible, changed section, and whether the workbook needs updates. | Do not contact the agency, register in a portal, or submit questions without separate approval. | needs_review
chg-002 | JEA Grant Administrator for Normandy Village Utility solicitation | package-controlled scope detail | The JEA page points bidders to the solicitation package for minimum qualifications, forms, and details. | Keep a placeholder for package-controlled requirements and prevent unsupported assumptions in the workbook. | No portal credentials or official bid package action. | needs_review
chg-003 | FloridaCommerce Infrastructure Repair Program | program guidance update | State program pages can update program notices, eligible activities, deadlines, or implementation guidance. | Record program-source URL, check date, changed guidance area, and affected workbook sections. | No eligibility decision or compliance interpretation. | sample_not_started
chg-004 | HUD CDBG-DR FAQs and 2 CFR Part 200 | reference-source refresh | Federal guidance and regulatory references anchor the evidence categories used by the sample. | Track whether source references were rechecked before a reviewer relies on the workbook. | No legal advice, procurement advice, or compliance certification. | sample_not_started

## Approval Dependencies
Approval Dependencies
Approval dependency tracker. This sheet does not represent approvals obtained.
Dependency ID | Dependency | Source Anchor | Why It Matters | Andy Support Output | Required Owner | Status | Boundary
dep-001 | FloridaCommerce approval or program-owner approval condition | City of Avon Park RFP #26-05 and FloridaCommerce CDBG-DR program surface | A selected grant-admin scope or contract can remain contingent on the responsible program owner's approval. | List approval checkpoints, owner, evidence needed, and open status. | qualified grant administrator or municipal program owner | needs_review | Do not represent that approval has been obtained.
dep-002 | HUD CDBG-DR and 2 CFR evidence review | HUD CDBG-DR FAQs and 2 CFR Part 200 | The support packet must stay behind a qualified reviewer for procurement, allowability, audit, and reporting judgments. | Organize evidence categories and missing-document flags. | qualified grant administrator, counsel, procurement owner, or finance owner | needs_review | No compliance opinion or allowability certification.
dep-003 | Official submission owner | JEA solicitation package boundary and public procurement norms | Only authorized parties should submit, certify, or approve official grant or procurement records. | Prepare internal readiness views and reviewer notes. | authorized public owner or prime grant administrator | blocked_until_approved | No official submission.
dep-004 | No-charge validation gate | route decision matrix | The lane only advances if a qualified reviewer confirms the artifact is useful and safely bounded. | Show one support-only workbook and record specific validation feedback. | Andy after explicit approval phrase | blocked_until_approved | No outreach without the exact approval phrase.

## Closeout Tracker
Closeout Tracker
Support-only closeout evidence map for qualified reviewer use.
Closeout ID | Phase | Required Evidence | Source Anchor | Support Task | Owner | Status | Boundary
close-001 | annual or periodic submissions | reporting calendar, responsible owner, supporting source-document index, unresolved issue log | City of Avon Park RFP #26-05 references grant administration support through program reporting and submissions. | Create a non-official calendar and evidence-readiness checklist for reviewer use. | qualified grant administrator or municipal program owner | sample_not_started | No official reporting.
close-002 | final closeout package | final reimbursement index, budget-to-actual reconciliation, procurement file index, payment proof, outstanding conditions | Avon Park CDBG-DR RFP and 2 CFR audit/readiness source categories | Track closeout packet completeness and unresolved evidence gaps. | qualified grant administrator | sample_not_started | No certification of closeout sufficiency.
close-003 | record retention and audit handoff | retention index, file location, responsible custodian, audit-reference notes | 2 CFR Part 200 includes audit requirements and record-support expectations. | Prepare an index of records and missing file flags for the official owner. | finance owner or records custodian | sample_not_started | Do not set official retention policy.
close-004 | monitoring or corrective-action follow-up | monitoring findings, corrective action owner, due dates, resolution evidence | CDBG-DR program management work commonly includes monitoring and closeout support. | Track open findings and evidence links without drafting official responses. | qualified grant administrator or public owner | sample_not_started | No official agency response.
close-005 | public records handoff | public-records file index, excluded sensitive fields note, access owner, file location | Florida public-sector grant work can be subject to public-records handling and later review. | Organize a public-records-safe handoff index and mark items requiring owner review. | public records custodian or municipal owner | sample_not_started | No public-records legal determination.

## Validation Questions
Human Validation Questions
Reviewer responses should decide whether to continue, narrow, or stop the lane.
Question ID | Question | Reviewer Response | Score | Follow-Up Action
q-001 | Would this tracker reduce time spent assembling reimbursement support?
q-002 | Which source-document fields are missing for a real CDBG-DR draw package?
q-003 | Where does this sample accidentally cross into grant-administrator responsibility?
q-004 | Would a fixed support packet be useful if it stayed behind the qualified grant administrator?
q-005 | What would make this safe enough to use on a live project?
Acceptance Criteria | Met? | Evidence
Qualified reviewer confirms at least one tracker/checklist would save time or reduce risk
Qualified reviewer identifies no unacceptable compliance overreach after boundary edits
Reviewer can name a real project situation where this would help
Reviewer does not require Andy to hold portal credentials or make official submissions
Reviewer suggests a clear support-only paid scope or says the lane is not useful

## Checks
Workbook Checks
These checks support artifact review only; they do not prove income.
Check | Formula / Value | Expected | Status
Proof status | $0 | $0
Tracker rows |  | 5
Checklist rows |  | 6
Risk rows |  | 4
Evidence map rows |  | 4
Source change rows |  | 4
Approval dependency rows |  | 4
Closeout rows |  | 5
Validation questions |  | 5
No official submission | Required | Required
No payment request | Required | Required